## Sheet1
AGM Counter (start from the bottom up) | Use this counter as a guide to the different deadlines arround your group's AGM to ensure you comply with the Group’s constitutional requirements.
Example AGM date (Enter date and press return) | 2023-11-03
Submit AGM minutes to CIfA | 2023-12-03 | Please submit up to one month after the AGM to meet Group regulations and keep your Group webpage up to date
Final AGM reminder and end of poll (if needed) | 2023-10-27 | Poll ends a week before the AGM to count votes and inform committee
Group members emailed AGM notice reminder and start of poll (if needed) | 2023-10-13 | CIfA's Group regulations require at least 21 days notice to inform group members, a larger notice period always benefits attendance. This is the latest date we can go ahead with the AGM.
End of call for nominations | 2023-09-29 | The last date we can accept nomination forms, usually two weeks before the AGM notice of 21 days. This will inform staff if a vote is needed or if any seats will need cooptions. Leave plenty of time for a vote. These are required when there is more than one nomination for one seat
Start of call for nominations | 2023-08-05 | Where seats on the committee are available for nominations. Prospective members can submit a completed nomination form by the deadline, usually to groups@archaeologists.net
Group members AGM notice to book and call for nominations | 2023-08-05 | Aim to give your group members as much notice as possible to get a well-attended AGM. This helps maintain interest in the group and for your committee to action ideas.
Confirm seats for nomination | 2023-08-05 | We have details of the committee members terms of office and will check this with the committee. If any member would like to step down, let staff know by this date. Existing committee members who were coopted or have completed their first term (3 years) need to complete a nomination form.
Confirm with staff AGM date | 2023-08-05 | Let us know your planned date well in advance (especially if you are holding an event with it). This helps avoid clashes between events/other AGMs and increases members interest in your meeting.